## Core Tests
Zea Voice ¦ Beta 1 core test checklist
P0 = release blocker; P1 = core behavior. Record evidence for every failure. Use staging and authorized test numbers.
Set Status and capture actual result, tester, test time (IST), call/task ID, and issue/evidence link. All cases start Not Started.
Test ID | Core area | Priority | Scenario | Test steps | Expected result | Status | Actual result / notes | Tester | Test date/time (IST) | Call / campaign / task ID | Issue / evidence link
CORE-01 | Call connection & audio | P0 | Inbound call | Call the assigned inbound number; speak and listen. | Agent answers; both sides hear clearly; correct agent is used. | Not Started
CORE-02 | Call connection & audio | P0 | Outbound and unanswered calls | Trigger outbound tests: answer one; leave one unanswered; reject one. | Correct destination; answered/no-answer/busy or provider-supported result recorded. | Not Started
CORE-03 | Call connection & audio | P0 | Hangup and capacity release | Test caller hangup, requested agent hangup, and authorized forced hangup. | Call ends; final status recorded; capacity released; no stuck call. | Not Started
CORE-04 | Call connection & audio | P1 | Recording and transcript | Download the recording and compare caller/agent speech with the transcript. | Audio is accessible only to authorized accounts; both sides captured; no unexplained omissions. | Not Started
CORE-05 | Conversation flow | P1 | Exact question and correction | Ask only the doctor name; correct the agent if it adds unwanted details. | Answers the exact question briefly; correction respected; no repeated unwanted response. | Not Started
CORE-06 | Conversation flow | P1 | Short replies and presence checks | Say yes/okay after agreeing to talk; say Hello during an ongoing conversation. | Interprets reply against last question; does not restart greeting or ask permission repeatedly. | Not Started
CORE-07 | Conversation flow | P0 | Long speech and interruption | Speak a long sentence with natural pauses; interrupt the agent; remain silent while it speaks. | No premature turn completion; real interruption handled; no false user speech or repeated audio. | Not Started
CORE-08 | Conversation flow | P1 | Tamil/Tanglish and closing | Speak natural Tamil/Tanglish; say no further help is needed. | Natural configured language; no name repeated every turn; agent closes without repeated questions. | Not Started
CORE-09 | Knowledge & pricing | P0 | Known service facts | Ask doctor name, hospital location, and supported services. Compare with approved KB. | Answers agree with approved KB; no invented services, experience or capabilities. | Not Started
CORE-10 | Knowledge & pricing | P0 | Current consultation fee | Ask current fee and what it covers; compare with configured live data. | Verified current amount, unit and exclusions; no historical or invented price. | Not Started
CORE-11 | Knowledge & pricing | P0 | Missing information | Ask a price or service detail absent from configured sources. | Clearly states uncertainty; does not fabricate facts or promise unsupported actions. | Not Started
CORE-12 | Knowledge & pricing | P1 | Developer answer sources | Check source details for factual answers as Developer; compare with retrieved content. | Sources support the answer; unexpected missing/wrong sources logged for investigation. | Not Started
CORE-13 | Contact & history | P1 | New name and returning greeting | State your own name; finish call; call again from the same number. | Verified name appears in conversation; returning greeting uses it once; no repeated name question. | Not Started
CORE-14 | Contact & history | P1 | Correct stored name | Say the stored name is wrong and provide your own corrected name. | Authorized update saves corrected name; later calls use it; no repeated correction loop. | Not Started
CORE-15 | Contact & history | P0 | Another patient | Request an appointment for a relative and provide their patient name. | Patient name retained for request; caller profile is not overwritten with relative name. | Not Started
CORE-16 | Contact & history | P1 | Reuse history and report name | Return with known name, phone and location; inspect conversation and Report Contact Name. | Briefly verifies known details; asks only missing fields; report name matches saved contact (log mismatch as defect). | Not Started
CORE-17 | Appointment/actions | P0 | Complete appointment intake | Request appointment; supply missing concern, visit preference, date and time; approve submission. | All required fields retained; configured submission verified; request is not falsely called a confirmed booking. | Not Started
CORE-18 | Appointment/actions | P1 | Interrupt and resume intake | Answer one intake field; ask service/fee question; then continue appointment request. | Answers interruption and resumes next missing field; never restarts intake. | Not Started
CORE-19 | Appointment/actions | P1 | Contact update during intake | Provide your own name during intake so update_contact executes; continue with location. | Tool completion retains goal and supplied fields; no premature anything-else closing. | Not Started
CORE-20 | Appointment/actions | P0 | Unavailable or failed action | Test missing submission tool or controlled tool failure in staging. | No claim of booking, saving, staff notification or delivery without verified success. | Not Started
CORE-21 | Callback | P0 | Relative callback | Request callback after 2 minutes while busy. Observe tool result, queue and call. | Exactly one saved task; one closing; hangup after playback; dispatch when due and eligible. | Not Started
CORE-22 | Callback | P0 | Change or cancel callback | Schedule callback; correct the time; separately test cancellation. | Latest request wins; no duplicate active callback; canceled task never dials. | Not Started
CORE-23 | Callback | P0 | Caller hangup and restart | Request callback; hang up after saved success. Restart worker before due time in staging. | Saved task survives hangup/restart; eligible callback dispatches once; no duplicate dialing. | Not Started
CORE-24 | Callback | P1 | Missed callback then inbound | Do not answer callback; call inbound afterward. | Uses verified history/current purpose; does not claim missed call was answered or task was saved from summary alone. | Not Started
CORE-25 | Campaign & queue | P0 | CSV destination accuracy | Upload known test contacts; inspect preview, import payload, tasks and dialed numbers. | Every queued/dialed number matches uploaded data; no old template contacts. | Not Started
CORE-26 | Campaign & queue | P1 | Invalid and duplicate rows | Import invalid numbers and duplicate phone rows; compare import counts with configured policy. | Invalid rows rejected visibly; duplicate policy applied consistently; counts reconcile. | Not Started
CORE-27 | Campaign & queue | P0 | 100 leads with limit 2 | Set company/campaign limit 2; inbound queue 100; outbound queue 1000; upload 100 authorized test leads. | At most 2 shared active calls; eligible remainder waits; slots reused; no loss/duplicates. | Not Started
CORE-28 | Campaign & queue | P0 | Schedule, controls and mixed traffic | Test schedule/timezone/retries; pause/resume/cancel; add inbound traffic; test wait limit. | No out-of-window campaign dialing; canceled tasks stay canceled; shared limit respected; configured waiting/timeout works. | Not Started
CORE-29 | Reports, billing & access | P0 | Call artifacts and outcomes | Compare final call status, transcript, recording, summary and verified tool outcomes. | Records match actual call; summary does not establish unsupported booking/callback success. | Not Started
CORE-30 | Reports, billing & access | P0 | Billing and duplicate events | Use known-duration calls; reconcile configured rates/Plivo rounding; replay callback in staging. | Expected cost and balance; no duplicate debit; distinguish platform charges from provider charges. | Not Started
CORE-31 | Reports, billing & access | P0 | Role and tab restrictions | Test User/Developer; disable tabs; attempt direct API access; test all tabs off and re-login. | Allowed tabs only; disabled actions denied; User cannot see cost/sources; existing role boundaries preserved. | Not Started
CORE-32 | Reports, billing & access | P0 | Company isolation and low credits | Use two companies; attempt cross-company IDs; exhaust test credits while tasks wait. | No cross-company records/actions; credit policy enforced; no unauthorized or duplicate calls. | Not Started