## Handover
Zea Voice ¦ Phase 1 Beta testing handover
Draft based on discussed functionality. Confirm deployed build, ownership, dates and client scope before sign-off.
Section | Requested information | Answer / testing guidance | Team confirmation / notes
1. BASIC INFORMATION | PROJECT NAME | Zea Voice — multi-company AI voice-agent application. Balaji Robotic Rehab Hospital is the initial testing configuration.
1. BASIC INFORMATION | VERSION | Phase 1 / Beta 1. Exact build number and deployed Git commit: confirm before handover.
1. BASIC INFORMATION | DEVELOPER NAME | Shanmugam / Zea Voice development team. Confirm the full contributor list.
1. BASIC INFORMATION | TESTING HANDOVER DATE | To be confirmed by Project Manager.
1. BASIC INFORMATION | PROJECT MANAGER | To be confirmed.
1. BASIC INFORMATION | PRIORITY | HIGH. Treat wrong-number dialing, unauthorized access, duplicate charges and false action confirmations as release blockers.
2. FEATURE | WHY WAS IT DEVELOPED? | Automate incoming/outgoing customer calls, approved enquiry answers, follow-up requests and company-scoped conversation history.
2. FEATURE | WHAT PROBLEM DOES IT SOLVE? | Missed enquiries, manual calling workload, inconsistent follow-up, scattered contact history and limited visibility into call outcomes.
2. FEATURE | WHO IS THE END USER? | Company Developers configuring agents; Company Users reviewing operational records; Super Admin managing the platform; customers/patients speaking with agents.
2. FEATURE | ACCESSIBILITY ROLES | Actual roles: Super Admin, Company Developer, Company User. Manager/Employee are not separate platform roles. Tab visibility is account-specific where deployed; role restrictions still apply.
3. SCOPE OF TESTING | FEATURES TO BE TESTED | Login and role permissions; agent prompt/voice saves; inbound/outbound audio; KB/live-data answers; interruption; contact/history reuse; configured appointment-request tools; callbacks; batch import; schedules/retries; shared capacity/queues; reports/recordings/billing; share-link expiry/revocation.
3. SCOPE OF TESTING | FEATURES TO BE TESTED LATER | WhatsApp calling, unconfigured CRM/staff notification/transfer workflows, additional languages/provider combinations, and higher concurrency than the approved Beta capacity. Confirm the Phase 1 scope with the PM.
3. SCOPE OF TESTING | ADDITIONAL FEATURES OUTSIDE CLIENT REQUIREMENT | Not established from the conversation. PM/client must confirm scope exclusions; do not classify platform features as extras without approval.
RE-TEST | MODIFIED FEATURES | Post-tool conversation context; contact-name/history reuse; callback scheduling and closing; TTS invalid-content handling; role-specific report visibility; per-account tab access; campaign permanent deletion. Verify each change exists in the deployed build.
RE-TEST | UI CHANGES | Conversation panels and expandable summaries; account tab toggles; permanent campaign-deletion warning with task counts and typed DELETE; User report cost/source visibility.
RE-TEST | BUGS FIXED — VERIFY IN RELEASE | Appointment context lost after update_contact; duplicate pre/post-tool speech; relative callback evidence rejection; punctuation-only acknowledgement TTS failure; old campaign waiting tasks after deletion. These require live regression, not assumed release approval.
RE-TEST | WORKFLOW CHANGES | Reuse known caller details; clarify corrections only; schedule callbacks through verified tools; enforce saved UI controls; permanently remove campaign/tasks only after guarded confirmation.
RE-TEST | FURTHER ENHANCEMENT | Review report contact-name mapping, detailed provider diagnostics, alerting and recovery, retrieval quality, and larger load tests. Confirm backlog and release priorities.
5. ADDITIONAL REQUIREMENTS | DARK / LIGHT / COLOURFUL MODE BUG REPORTING | YES: include a Theme field per issue and test both implemented light/dark modes. Colourful mode: not confirmed; mark Not Applicable unless available in the release. Separate issue only if root causes differ.
5. ADDITIONAL REQUIREMENTS | FAILURE EVIDENCE | Record test ID, steps, expected/actual result, role, company, theme, timestamp (IST), Call/Campaign/Task ID, screenshots and relevant sanitized logs.
5. ADDITIONAL REQUIREMENTS | RELEASE ACCEPTANCE | No unresolved critical access, dialing, billing or action-confirmation failures. Verify migration, backups, rollback and configured provider limits. All deployment checks need recorded evidence.
6. TEST DATA | SAMPLE DEVELOPER LOGIN | Website: https://voice.zeacrm.com/ ¦ Developer email: support@balajiroboticrehab.com. Share the current password separately through an approved secure channel; no password included in this workbook.
6. TEST DATA | SAMPLE COMPANY USER LOGIN | User email: dr.nithya@balajiroboticrehab.com. Confirm active role and assigned company. Share current password separately. Super Admin credentials: obtain from authorized owner.
6. TEST DATA | SAMPLE TASKS | An appointment request interrupted by a fee question; callback after 2 minutes; callback reschedule/cancel; returning contact enquiry; 100 unique authorized test leads with company/campaign concurrency 2.
6. TEST DATA | VALID EXAMPLES | CSV headers: name,phone,remarks. Full E.164 phone stored as text. Use consented team-owned numbers. Test known doctor/service facts, current verified fees and explicit caller-name corrections.
6. TEST DATA | INVALID EXAMPLES | Blank/malformed/scientific-notation phone; duplicate normalized phone; missing phone column; invalid date or ambiguous time; unavailable tool; expired/revoked share link; disabled tab; cross-company ID; insufficient credits.
6. TEST DATA | LOAD / QUEUE SETUP | Company concurrency 2; campaign concurrency 2; inbound waiting capacity 100; outbound waiting capacity 1000. 100 unique valid leads: at most 2 active, remaining eligible tasks wait. Inbound/outbound share slots; schedule/credits/provider limits still apply.
6. TEST DATA | DUPLICATE IMPORT EXPECTATION | 100 file rows containing only 2 unique valid phone numbers produce 2 accepted tasks and 98 duplicates. File row count is not accepted-lead count.
6. TEST DATA | SAFETY AND PRIVACY | Use staging where possible, approved test contacts and synthetic patient data. Do not use random generated phone numbers, real medical records or secrets in shared bug reports.

## Role Permissions
4. User roles and permissions
Use actual platform roles instead of Admin / Manager / Employee. Verify restrictions against the deployed build.
Feature | Super Admin | Company Developer | Company User | Test result / notes
Platform companies / providers / credits | YES | NO | NO
Create/edit accounts and assign tab access | YES | NO | NO
Company Dashboard / Analytics | YES — company context | YES — if enabled | YES — if enabled
Agent configuration and attached resources | YES — authorized company context | YES — if enabled | Read-only where exposed; no configuration management
Campaign create/edit/pause/delete | YES — company context | YES — if enabled | Read-only; no management
Call Queue viewing | YES — company context | YES — if enabled | YES — if enabled
Cancel waiting tasks / resume campaigns | YES — company context | YES — if enabled | NO
Conversation / transcript / recording access | YES — company context | YES — if enabled | YES — company-scoped, if enabled
Reports: Call Cost / Answer Sources | YES | YES — report access required | NO
Phone-number viewing | YES | YES — if enabled | YES — if enabled
API Keys / Settings / Integrations tabs | YES — applicable administrative access | YES — if enabled | NO
Public agent calling share page | Valid link only | Valid link only | Valid link only
Access another company without authorization | NO | NO | NO